## Sheet1
Item # | Description | Estimated Time | By
Very High Priority
1 | Import and export data from database | 300
2 | Find few closest parking spots by birds-eye-view proximity | 200 |  | Deliverable | Proiority
3 | Rank close parking spots by driving distance | 100 |  | Database IO | Very High
3.1 | Know driving distance between any two points | 400 |  | Search Algorithm | Very High
High Priority |  |  |  | Sortest Path | Very High
4 | User interface | 200
6 | Determine paid vs free parking spots | 50
5 | Determine user location (automatic or manual?) | 150 |  | Sort Algorithm | Very High
Medium Priority |  |  |  | Front End | Medium
4.1 | Useful/attractive front end app implementation | 250
5.1 | Read additional information from the sign and show to user interface | 70